# Supplier Commitment Log - Regional Telecom Recovery

Document control: SCL-2026-07-15. All entries marked Signed are binding for the recovery review. Entries marked Unsigned or Rejected must not be treated as approved commitments or approved incremental cost.

# Section 1 - Signed Supplier Commitments

| Ref | SKU | Supplier | Signed status | Committed qty | Due at hub | Approved incremental cost USD | Linked site or group | Decision note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SC-101 | RRU-64T-A | RadioWorks | Signed | 8 | 2026-07-25 | 3200 | ST-001 to ST-008 priority pool | Supersedes PO-4001 quantity 12 and ETA 2026-07-20. Remaining quantity is not signed. |
| SC-102 | RRU-64T-B | RadioWorks | Signed | 6 | 2026-07-28 | 4500 | Firmware-ready non-legacy sites only | Supersedes PO-4002 snapshot. Eligibility still governed by allocation_policy_memo.pdf. |
| SC-103 | CAB-OD-42U | CabinetCo | Signed | 4 | 2026-08-05 | 2800 | ST-009 to ST-012 | Signed due date after recovery target. Use if no open carrier exception changes it. |
| SC-104 | CAB-OD-42U-S | CabinetCo | Signed | 5 | 2026-07-24 | 3750 | Non-coastal substitute candidates | CabinetCo confirms sealed variant is not released for coastal salt-spray zones. |
| SC-105 | PWR-RECT-3K-R | PowerGrid | Signed | 6 | 2026-07-26 | 6600 | ST-006, ST-018, ST-028 and approved alternates | Requires site-level power engineer approval. Approved cost can trigger Cost Approval status. |
| SC-106 | FTK-24F-L | FiberLink | Signed | 10 | 2026-07-23 | 1500 | Long-tail fibre candidates | Use only for cable-tail length 15 m or greater. |
| SC-107 | FTK-24F | FiberLink | Signed | 5 | 2026-08-06 | 1250 | Late fibre replenishment pool | Due date after recovery target. Do not use for target-ready release. |
| SC-108 | RRU-64T-B | RadioWorks | Signed | 5 | 2026-07-30 | 5200 | Epsilon cluster substitute pool | Open carrier exception CX-2206 controls final availability. |
| SC-109 | CAB-OD-42U | CabinetCo | Signed | 6 | 2026-07-29 | 4200 | Gamma and Delta cabinet recovery pool | Supersedes PO-4009 snapshot ETA 2026-08-02. |
| SC-110 | PWR-RECT-3K | PowerGrid | Signed | 8 | 2026-07-29 | 0 | Gamma and Delta power recovery pool | Baseline replenishment with no incremental cost. |
| SC-112 | FTK-24F-L | FiberLink | Signed | 4 | 2026-07-27 | 2200 | ST-027, ST-028, ST-031, ST-032 | Open carrier exception CX-2204 controls final availability. |

# Section 2 - Unsigned, Rejected, or Incomplete Supplier Requests

| Ref | SKU | Supplier | Status | Requested qty | Requested due at hub | Requested cost USD | Linked site or group | Decision note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SC-201 | RRU-64T-A | RadioWorks | Unsigned | 10 | 2026-08-05 | 0 | Delta and Epsilon sites | Matches PO-4011. No signed commitment. Carry as follow-up only. |
| SC-202 | CAB-OD-30U | CabinetCo | Rejected | 4 | 2026-07-18 | 0 | ST-030 and ST-035 | Not an approved cabinet substitute for this rollout. |
| SC-203 | FTK-24F emergency lot | FiberLink | Unsigned | 3 | 2026-07-28 | 900 | ST-023 and ST-027 | Request lacks shipment number and cannot support release. |
| SC-204 | PWR-RECT-3K-R extra lot | PowerGrid | Unsigned | 4 | 2026-08-01 | 4800 | ST-031 to ST-036 | No power engineer approval list provided. |
| SC-205 | RRU-64T-B firmware waiver | RadioWorks | Rejected | 2 | 2026-07-29 | 1800 | ST-008 and ST-025 | Policy team rejected use on legacy BBU sites. |

# Section 3 - Supplier Accountability Notes

RadioWorks is accountable for RRU-64T-A and RRU-64T-B delivery commitments.

CabinetCo is accountable for CAB-OD-42U and CAB-OD-42U-S delivery commitments.

PowerGrid is accountable for PWR-RECT-3K and PWR-RECT-3K-R delivery commitments.

FiberLink is accountable for FTK-24F and FTK-24F-L delivery commitments.

Signed due dates in this log override purchase-order snapshot dates, except where carrier_exception_digest.pdf lists an open carrier exception with a later revised ETA.